Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 19 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS78575 |
| Project Name | shopsmart: your digital grocery store experience |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story No | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Authentication | US-1 | User can register with email & password | 3 | High |
| Sprint-1 | Authentication | US-2 | User can login securely | 2 | High |
| Sprint-1 | Admin | US-3 | Admin login with predefined credentials | 2 | High |
| Sprint-1 | UI | US-4 | Create homepage & navigation | 3 | Medium |
| Sprint-1 | UI | US-5 | Display product list | 5 | High |
| Sprint-1 Total |  |  |  | 15 |  |
| Sprint-2 | Functional Requirement | User Story No | User Story | Story Points | Priority |
| Sprint-2 | Product | US-6 | Admin add product | 5 | High |
| Sprint-2 | Product | US-7 | Admin edit/delete product | 5 | High |
| Sprint-2 | Product | US-8 | Product details page | 4 | Medium |
| Sprint-2 | Search | US-9 | Product search/filter | 6 | Medium |
| Sprint-2 Total |  |  |  | 20 |  |
| Sprint-3 | Functional Requirement | User Story No | User Story | Story Points | Priority |
| Sprint-3 | Cart | US-10 | Add to cart | 5 | High |
| Sprint-3 | Cart | US-11 | Update/remove cart items | 5 | High |
| Sprint-3 | Order | US-12 | Checkout process | 6 | High |
| Sprint-3 | Order | US-13 | Order placement | 4 | High |
| Sprint-3 Total |  |  |  | 20 |  |
| Sprint-4 | Functional Requirement | User Story No | User Story | Story Points | Priority |
| Sprint-4 | Orders | US-14 | Order history | 5 | Medium |
| Sprint-4 | Orders | US-15 | Admin view all orders | 5 | High |
| Sprint-4 | Payment | US-16 | Payment integration | 6 | Medium |
| Sprint-4 | Email | US-17 | Email confirmation | 4 | Medium |
| Sprint-4 Total |  |  |  | 20 |  |

Project Tracker, Velocity & Burndown Chart:

| Sprint | Total Story Points | Duration | Start | End (Planned) | Completed | Actual |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 7 days | Day 1 | Day 7 | 20 | Day 7 |
| Sprint-2 | 20 | 7 days | Day 8 | Day 14 | 18 | Day 14 |
| Sprint-3 | 20 | 7 days | Day 15 | Day 21 | 16 | Day 21 |
| Sprint-4 | 20 | 7 days | Day 22 | Day 28 | 14 | Day 28 |

Velocity:

Total completed story points = 20 + 18 + 16 + 14 = 68

Number of sprints = 4

Average Velocity = 68 / 4 = 17 story points per sprint

If sprint duration = 7 days:

Velocity per day = 17 / 7 ≈ 2.4 points/day

Burndown Chart: